## MRS
Group 4 - SENTINAILS | SENTINAILS
| Group | SENTINAILS |  |  | DEPARTMENT |  |  |  | Computer Engineering
| SEMESTER | 2nd Semester |  |  | SY |  |  |  | 2025-2026
ID | TASK | START DATE | DUE DATE | STATUS | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18
[5 empty] | 11/29 | 11/30 | 12/6 | 12/7 | 12/8 | 12/9 | 12/10 | 12/11 | 12/12 | 12/13 | 12/14 | 12/15 | 12/16 | 12/17 | 12/18 | 12/19 | 12/20 | 12/21 | 12/22 | 12/23 | 12/24 | 12/25 | 12/26 | 12/27 | 12/28 | 12/29 | 12/30 | 12/31 | 1/1 | 1/2 | 1/3 | 1/4 | 1/5 | 1/6 | 1/7 | 1/8 | 1/9 | 1/10 | 1/11 | 1/12 | 1/13 | 1/14 | 1/15 | 1/16 | 1/17 | 1/18 | 1/19 | 1/20 | 1/21 | 1/22 | 1/23 | 1/24 | 1/25 | 1/26 | 1/27 | 1/28 | 1/29 | 1/30 | 2/01 | 2/02 | 2/03 | 2/04 | 2/05 | 2/06 | 2/07 | 2/08 | 2/09 | 2/10 | 2/11 | 2/12 | 2/13 | 2/14 | 2/15 | 2/16 | 2/17 | 2/18 | 2/19 | 2/20 | 2/21 | 2/22 | 2/23 | 2/24 | 2/25 | 2/26 | 2/27 | 2/28 | 3/1 | 3/2 | 3/3 | 3/4 | 3/5 | 3/6 | 3/7 | 3/8 | 3/9 | 3/10 | 3/11 | 3/12 | 3/13 | 3/14 | 3/15 | 3/16 | 3/17 | 3/18 | 3/19 | 3/20 | 3/21 | 3/22 | 3/23 | 3/24 | 3/25 | 3/26 | 3/27 | 3/28 | 3/29 | 3/30 | 3/31 | 4/1 | 4/2 | 4/3 | 4/4 | 4/5 | 4/6 | 4/7 | 4/8 | 4/9
1 | Planning Phase
1.1 | Brainstorming | 2025-11-29 | 2025-12-06 | Done | bar: WEEK 1 11/29 to WEEK 1 12/6
1.2 | Researching | 2025-11-29 | 2025-12-06 | Done | bar: WEEK 1 11/29 to WEEK 1 12/6
1.3 | Conceptualization | 2025-11-29 | 2025-12-06 | Done | bar: WEEK 1 11/29 to WEEK 1 12/6
1.4 | Searching for possible client | 2025-11-29 | 2025-12-06 | Done | bar: WEEK 1 11/29 to WEEK 1 12/6
1.5 | Background checking of the possible client | 2025-11-29 | 2025-12-06 | Done | bar: WEEK 1 11/29 to WEEK 1 12/6
2 | Requirements
2.1 | Making of survey | 2025-12-06 | 2025-12-13 | Done | bar: WEEK 1 12/7 to WEEK 2 12/13
2.2 | Selecting of the client | 2025-12-06 | 2025-12-13 | Done | bar: WEEK 1 12/7 to WEEK 2 12/13
2.3 | Dissemination of survey forms | 2025-12-06 | 2025-12-13 | Done | bar: WEEK 1 12/7 to WEEK 2 12/13
2.4 | Interviewing the client | 2025-12-13 | 2025-12-20 | Done | bar: WEEK 2 12/13 to WEEK 3 12/19
2.5 | Analyzing and interpreting the data | 2025-12-13 | 2025-12-20 | Done | bar: WEEK 2 12/13 to WEEK 3 12/19
3 | Design Phase
3.1 | Algorithm | 2025-12-20 | 2025-12-27 | Done | bar: WEEK 3 12/20 to WEEK 3 12/23
3.2 | Flowchart | 2025-12-20 | 2025-12-27 | Done | bar: WEEK 3 12/20 to WEEK 3 12/23
3.3 | DFD (Data Flow Diagram) | 2026-03-01 | 02/28/2026 | On Going | bar: WEEK 5 1/3 to WEEK 11 2/14
3.4 | ERD (Entrity-Relationship Diagram) | 2026-03-01 | 02/28/2026 | On Going | bar: WEEK 5 1/3 to WEEK 11 2/14
3.5 | Storyboarding | 2026-03-01 | 02/28/2026 | On Going | bar: WEEK 5 1/3 to WEEK 11 2/14
4 | Development Phase
4.1 | HTML, CSS and JS Coding of User Interface | 2026-10-01 | 2026-07-03 | On Going | bar: WEEK 6 1/10 to WEEK 11 2/14
4.2 | HTML, CSS and JS Coding Front End | 2026-10-01 | 2026-07-03 | On Going | bar: WEEK 6 1/10 to WEEK 11 2/14
4.3 | MySQL and PYTHON Coding Back End | 2026-10-01 | 2026-07-03 | On Going | bar: WEEK 6 1/10 to WEEK 11 2/14
4.4 | System Testing | 01/24/2026 | 2026-07-03 | On Going | bar: WEEK 8 1/24 to WEEK 11 2/14
4.5 | Debugging | 01/24/2026 | 2026-07-03 | On Going | bar: WEEK 8 1/24 to WEEK 11 2/14
5 | QA & Testing
5.1 | Multiple Device Test | 2026-07-03 |  | Queue | bar: WEEK 1 11/29 to WEEK 11 2/14
5.2 | Beta Testing | 2026-07-03 |  | Queue | bar: WEEK 1 11/29 to WEEK 11 2/14
6 | Deployment & Maintenance
6.1 | Authoring Privacy Policies and User Manual |  |  | Queue | bar: WEEK 1 11/29 to WEEK 11 2/14
6.2 | Deployment |  |  | Queue | bar: WEEK 1 11/29 to WEEK 11 2/14
6.3 | Maintenance |  |  | Queue | bar: WEEK 1 11/29 to WEEK 11 2/14
7 | Documentation
7.1 | Chapter 1: Introduction | 12/13/2025 | 2026-01-03 | Done | bar: WEEK 2 12/13 to WEEK 5 1/3
7.2 | Chapter 2: Review of Related Literature and Studies | 2026-01-03 |  | On Going | bar: WEEK 5 1/3 to WEEK 11 2/14
7.3 | Chapter 3: Methodology |  |  | Queue | bar: WEEK 1 11/29 to WEEK 11 2/14
7.4 | Chapter 4: Results and Discussion |  |  | Queue | bar: WEEK 1 11/29 to WEEK 11 2/14
7.5 | Chapter 5: Conclusion |  |  | Queue | bar: WEEK 1 11/29 to WEEK 11 2/14
7.6 | Final Paper Check |  |  | Queue | bar: WEEK 1 11/29 to WEEK 11 2/14
7.7 | Defense |  |  | Queue | bar: WEEK 1 11/29 to WEEK 11 2/14